## Test Plan
Section | Detail
Project | OpenCart Demo - E-commerce QA
Scope | Register, Login, Search, Add to Cart, Checkout, Order Confirmation
Test Types | Functional, UI, Positive/Negative, Integration (API & DB)
Environment | https://demo.opencart.com/ (Public demo)
Tools | Spreadsheet, Postman, Playwright, SQL, Jira
Schedule | Estimated 5 working days for full regression baseline
Owner | Bahtiar Eka Permana

## Detail
Section | Description
1. Introduction | This Test Plan defines the strategy, scope, objectives, resources, and schedule of all testing activities for the OpenCart Demo E-commerce project.
2. Objectives & Scope | In Scope: Registration, Login, Search, Add to Cart, Checkout, Order Confirmation. Out of Scope: Payment gateway integration, email delivery, SMS notification.
3. Test Strategy | Manual Testing for functional and UI validation. API Testing using Postman. Automation using Playwright. Database validation with SQL queries.
4. Test Levels | Unit Testing (by developers), System Testing, Regression Testing, and User Acceptance Testing (if applicable).
5. Test Environment | Environment URL: https://demo.opencart.com/ Browsers: Chrome v131, Edge v130 Operating Systems: macOS, Windows 11 Test Data: Dummy users and products.
6. Roles & Responsibilities | QA Engineer: Bahtiar Eka Permana – Test execution, defect reporting.
7. Entry & Exit Criteria | Entry Criteria: Environment ready, test data prepared, build deployed successfully. Exit Criteria: All test cases executed, 95% pass rate achieved, no critical defects open.
8. Risks & Mitigation | Risk: Demo site downtime – High – Mitigation: Schedule testing during off-peak hours. Risk: Network latency – Medium – Mitigation: Use stable Wi-Fi. Risk: API access restricted – High – Mitigation: Use mock data if necessary.
9. Deliverables | Test Plan, Test Cases, Test Execution Report, Bug Report, Postman Collection, Playwright Automation Suite.
10. Defect Severity & Priority Matrix | Critical: Blocks system operation or causes crash. High: Major functionality failure without workaround. Medium: Partial failure with workaround available. Low: Minor issue not affecting functionality. Priority: P1 – Must fix before release. P2 – Fix in next release. P3 – Fix when time permits.